## PROJECT_DATA
IoC Process Manager — Sample Project Data · Thornfield Court Residential Development
PROCESS ID | NAME | METHOD | ACTOR | ACTOR ORG | START DATE | END DATE | PREDECESSORS | RESOURCES | INPUT MATERIALS | OUTPUT ELEMENTS | SPACE | STATUS | PROGRESS | NOTES
PHASE 1 — PRE-CONSTRUCTION & ENABLING
P01 | Topographic & Boundary Survey | Total Station Survey + GPS | Ahmed Al-Rashid | GeoSurvey Associates | 2025-03-03 | 2025-03-05 |  | Total Station, GPS Rover |  | Topographic Survey Drawing | Full Site | finished | 100 | Establish OS grid coordinates, boundary pegs, site datum TBM
P02 | Ground Investigation & Borehole Drilling | Rotary Borehole Drilling | Ingrid Bergman | SoilTech Investigations | 2025-03-06 | 2025-03-14 | P01 | Cable Percussion Rig, Rotary Drill |  | Geotechnical Report, Trial Pit Logs | Full Site | finished | 100 | 6 boreholes to 12m, 3 trial pits, lab analysis for bearing capacity
P03 | Demolition of Existing Structures | Selective Mechanical Demolition | James Kowalski | ClearSite Demolition Ltd | 2025-03-10 | 2025-03-21 | P01 | Excavator with Demolition Attachment, Skip Lorries | Existing Masonry, Concrete Rubble | Cleared Site | Full Site | finished | 100 | Demolish 2 derelict agricultural outbuildings, remove foundations
P04 | Temporary Site Hoarding & Security | Hoarding Erection | James Kowalski | ClearSite Demolition Ltd | 2025-03-10 | 2025-03-12 | P01 | Heras Fencing, Hoarding Panels | Hoarding Timber, Security Posts | Site Perimeter Hoarding | Site Perimeter | finished | 100 | 2.4m hoarding with security lighting, welfare unit, site office
P05 | Temporary Services & Site Setup | Temporary Services Installation | Maria Okonkwo | BuildServ Site Services | 2025-03-13 | 2025-03-17 | P04 | Generator, Water Bowser | Ducting, Cable, Pipework | Temporary Power & Water Supply | Site Office Area | finished | 100 | Temporary 3-phase power, water supply, sewage settlement tank
P06 | Ecology Survey & Tree Protection | Ecological Assessment | Dr. Sarah Chen | EcoSurveys UK Ltd | 2025-03-06 | 2025-03-10 | P01 |  |  | Ecological Survey Report, Tree Protection Order Plan | Full Site | finished | 100 | Phase 1 habitat survey, bat/bird surveys, TPO compliance plan
P07 | Building Regulations Approval & Notifications | Statutory Approval Process | Helen Marchetti | HM Architecture Ltd | 2025-03-03 | 2025-03-28 |  |  |  | Building Regulations Full Plans Approval | Off Site | finished | 100 | Full Plans submission to Local Authority Building Control
PHASE 2 — SUBSTRUCTURE & FRAME
P08 | Bulk Excavation to Formation Level | Open-cut Bulk Excavation | James Kowalski | ClearSite Demolition Ltd | 2025-04-07 | 2025-04-18 | P02;P03;P07 | 360° Tracked Excavator (20T), Dumper Trucks | Excavated Spoil | Excavated Formation | Full Footprint | finished | 100 | Cut to 1.8m formation level, cart spoil off-site, stockpile retained material
P09 | Sheet Piling — Perimeter Retention | Vibrated Steel Sheet Piling | Kofi Asante | DeepFix Piling Ltd | 2025-04-07 | 2025-04-14 | P02;P07 | Piling Rig (APE200), Crane | FSP4 Sheet Piles, Walings | Sheet Pile Retaining Wall | Perimeter Boundary | finished | 100 | 100m perimeter sheet pile wall, 8m depth, tie-back anchors at 4m centres
P10 | Reduced Level Excavation & Trimming | Precision Machine Excavation | James Kowalski | ClearSite Demolition Ltd | 2025-04-22 | 2025-04-25 | P08;P09 | 360° Excavator (13T), Dumper |  | Trimmed Formation Level | Foundation Zones | finished | 100 | Hand trim to 300mm of formation, proof roll with vibrating roller
P11 | Reinforcement Cage Fabrication & Fix — Pad Foundations | Rebar Cage Fixing | Kofi Asante | DeepFix Piling Ltd | 2025-04-28 | 2025-05-07 | P10 | Bar Bender, Bar Cutter, Crane | B500B 20mm Rebar, Link Bars, Spacers | Reinforcement Cage — Pad Foundations | Foundation Zones | finished | 100 | 24 pad foundations, H20@150 BRC, 75mm blinding, Visqueen DPM
P12 | Concrete Pour — Pad Foundations | Ready-mix Concrete Placement | Tom Brennan | PourRight Concrete Ltd | 2025-05-08 | 2025-05-09 | P11 | Concrete Pump (36m Boom), Vibrating Poker | C32/40 Ready-mix Concrete | Reinforced Concrete Pad Foundations | Foundation Zones | finished | 100 | C32/40 XC2, 24 pads, pump pour, vibrate, cure 7 days minimum
P13 | Drainage — Below Ground Foul & Surface Water | Gravity Drainage Installation | Lena Cavalcanti | PipeSafe Civil Drainage | 2025-05-12 | 2025-05-23 | P10 | Mini Excavator, Laser Level | UPVC 150/225mm Pipes, Manholes, Gravel | Below-Ground Drainage Network | Full Footprint | finished | 100 | Foul drain to adopted sewer, surface water to attenuation tank
P14 | Ground Beams — Reinforcement & Formwork | Rebar Fixing & Timber Formwork | Kofi Asante | DeepFix Piling Ltd | 2025-05-13 | 2025-05-21 | P12 | Crane, Formwork Kit | B500B Rebar, Timber Formwork | Reinforcement Cage — Ground Beams | Foundation Zones | finished | 100 | Ring and tie beams linking pad foundations, formwork strike 3 days
P15 | Concrete Pour — Ground Beams | Ready-mix Concrete Placement | Tom Brennan | PourRight Concrete Ltd | 2025-05-22 | 2025-05-22 | P14 | Concrete Pump | C32/40 Ready-mix Concrete | Reinforced Concrete Ground Beams | Foundation Zones | finished | 100 | C32/40 ground beams, continuous pour, curing compound applied
P16 | Hardcore Fill & Ground Floor Slab Preparation | Hardcore Compaction | Maria Okonkwo | BuildServ Site Services | 2025-05-26 | 2025-06-03 | P13;P15 | Vibrating Plate, Roller | Type 1 MOT Hardcore, Sand Blinding | Compacted Hardcore Sub-base | Ground Floor Zone | finished | 100 | 300mm Type 1 MOT compacted in 150mm layers, 50mm sand blinding, Visqueen
P17 | Ground Floor Slab — Reinforcement, Pour & Cure | Slab Reinforcement & Ready-mix Pour | Tom Brennan | PourRight Concrete Ltd | 2025-06-04 | 2025-06-06 | P16 | Concrete Pump, Power Float | B500A Mesh A393, C28/35 Concrete, Fibres | Reinforced Ground Floor Slab | Ground Floor | finished | 100 | 200mm RC slab, A393 mesh, 25mm cover, power float finish, 28-day cure
PHASE 3 — SUPERSTRUCTURE & ENVELOPE
P18 | Structural Steelwork — Erection | Structural Steel Frame Erection | Piotr Zielinski | SteelFab Structures Ltd | 2025-06-16 | 2025-07-04 | P17 | Mobile Crane (50T), Bolt Torque Wrenches, MEWP | Grade S355 UB/UC Sections, HSFG Bolts | Primary Steel Frame | Full Building Footprint | finished | 100 | 4-storey primary steel frame, 24 columns, 3 floor plates, HSFG bolt connections
P19 | Precast Concrete Floor Planks — Supply & Install | Precast Concrete Installation | Piotr Zielinski | SteelFab Structures Ltd | 2025-07-07 | 2025-07-18 | P18 | Mobile Crane (50T), Vacuum Lifter | 200mm Hollowcore Planks, Structural Grout | Precast Hollowcore Floor Slabs | Floor Levels 1-3 | finished | 100 | 200mm hollowcore planks, 75mm structural screed topping, grouted joints
P20 | Structural Screed Topping — Floors 1-3 | Structural Screed Application | Tom Brennan | PourRight Concrete Ltd | 2025-07-21 | 2025-07-25 | P19 | Forced Action Mixer, Pump | C28/35 Structural Screed, Mesh | Structural Screed Topping | Floor Levels 1-3 | finished | 100 | 75mm bonded screed over hollowcore, B503 mesh, pump applied
P21 | Masonry — External Cavity Walls | Cavity Wall Masonry | Bogdan Nowak | MasonCraft Brickwork Ltd | 2025-07-07 | 2025-08-01 | P18 | Scaffold (Kwikstage System), Mixer | Buff Facing Brick, Dense Concrete Block, Ties, DPC | External Cavity Walls | Building Perimeter | finished | 100 | 102mm facing brick / 100mm block cavity wall, 100mm PIR insulation, wall ties
P22 | Roof Structure — Timber Trusses & Decking | Timber Roof Truss Erection | Luca Ferreira | TimberFrame Solutions | 2025-08-04 | 2025-08-15 | P20;P21 | Mobile Crane, Nail Guns | C24 Trussed Rafters, OSB3 Decking, Ridge Board | Timber Roof Structure | Roof Level | finished | 100 | Prefabricated attic trusses at 600c/c, OSB3 sarking, temporary weatherproofing
P23 | Roof Covering — Slate & Lead Flashing | Natural Slate Roofing | Dean O'Sullivan | Apex Roofing Contractors | 2025-08-18 | 2025-09-05 | P22 | Scaffold, Lead Dressing Tools | Welsh Slate 500x250, Lead Code 4/5, Underlayer | Completed Roof Covering | Roof Level | finished | 100 | Natural Welsh slate, code 4 lead valleys/flashings, code 5 parapet caps
P24 | External Windows & Doors — Supply & Fix | Timber Window & Door Installation | Luca Ferreira | TimberFrame Solutions | 2025-08-18 | 2025-09-05 | P22 | MEWP, Silicone Applicator | Softwood Double-glazed Units, EPDM Seals | Installed Timber Windows & Doors | Building Perimeter | finished | 100 | 52 No. softwood casement windows, 8 No. external doors, double-glazed, factory primed
P25 | External Render & Insulated Cladding | EWI System Application | Bogdan Nowak | MasonCraft Brickwork Ltd | 2025-09-08 | 2025-09-26 | P23;P24 | Scaffold | EPS 100mm Board, Render Base Coat, Silicone Topcoat | External Insulated Render Finish | Building Perimeter | started | 40 | EWI 100mm EPS, mesh-reinforced basecoat, silicone render finish
P26 | Roof Insulation & Air Tightness | Blown Insulation Installation | Dean O'Sullivan | Apex Roofing Contractors | 2025-09-01 | 2025-09-05 | P23 | Blown Insulation Machine | 400mm Mineral Wool Blown Insulation, VCL | Insulated & Airtight Roof | Roof Level | finished | 100 | 400mm blown mineral wool to roof void, VCL to ceiling level, airtightness taping
P27 | External Landscaping — Phase 1 Enabling | Landscape Enabling Works | Maria Okonkwo | BuildServ Site Services | 2025-09-15 | 2025-09-26 | P25 | Mini Excavator, Vibrating Plate | Sharp Sand, MOT Type 1, Edging | Prepared Landscape Sub-base | External Areas | planned | 0 | Sub-base for paths and parking, topsoil strip and retain, boundary fencing
PHASE 4 — FIT-OUT & COMPLETION
P28 | 1st Fix Plumbing — Pipework & Waste | First Fix Plumbing | Lena Cavalcanti | PipeSafe Civil Drainage | 2025-09-08 | 2025-09-19 | P24;P26 | Pipe Bender, Soldering Kit | 22mm/15mm Copper Pipe, UPVC Waste, Brackets | 1st Fix Plumbing Installation | All Floors | started | 70 | HW/CW distribution to all apartments, soil stacks, MVHR ductwork routes
P29 | 1st Fix Electrical — Containment & Wiring | First Fix Electrical | Derek Walsh | ElecFit Electrical Contractors | 2025-09-08 | 2025-09-26 | P24;P26 | Cable Puller, Drill | 2.5mm T&E Cable, 4mm Ring Main Cable, Conduit | 1st Fix Electrical Installation | All Floors | started | 55 | Sub-mains, ring mains, lighting circuits, data/TV containment, EV charger routes
P30 | Thermal & Acoustic Insulation — Floors & Partitions | Insulation Installation | Luca Ferreira | TimberFrame Solutions | 2025-09-15 | 2025-09-26 | P28;P29 |  | 60mm Acoustic Quilt, 100mm Rockwool, VCL | Insulated Floor & Partition Build-up | All Floors | planned | 0 | 60mm acoustic quilt between floors, 100mm Rockwool to party walls, VCL
P31 | Internal Blockwork Partitions | Blockwork Partition Construction | Bogdan Nowak | MasonCraft Brickwork Ltd | 2025-09-15 | 2025-10-03 | P28;P29 | Mixer, Scaffold | 100mm Dense Aggregate Block, Mortar, DPC | Internal Blockwork Partitions | All Floors | planned | 0 | 100mm dense block partitions to all apartments, lintels over openings
P32 | Plasterboard Dry Lining & Ceilings | Plasterboard Installation | Piotr Zielinski | SteelFab Structures Ltd | 2025-10-06 | 2025-10-24 | P30;P31 | Drywall Screw Gun, Stilts | 12.5mm Plasterboard, 15mm FB, Metal Frame | Plasterboard Lining & Suspended Ceiling | All Floors | planned | 0 | Metal stud lining, 12.5mm board, 15mm FB to ceilings, taped and jointed
P33 | Wet Plaster Skim & Finish | Two-coat Plaster Skim | Bogdan Nowak | MasonCraft Brickwork Ltd | 2025-10-27 | 2025-11-14 | P32 | Mixing Drill, Plastering Hawk | Finish Plaster, PVA Bond | Plaster Skim Finish | All Floors | planned | 0 | 2mm finish skim to all plasterboard, set and polish to 3mm tolerance
P34 | 2nd Fix Plumbing — Sanitaryware & Commissioning | Second Fix Plumbing | Lena Cavalcanti | PipeSafe Civil Drainage | 2025-11-17 | 2025-11-28 | P33 | Pressure Test Kit | Sanitaryware, Basin Mixers, Shower Valves, Radiators | 2nd Fix Plumbing & Sanitaryware | All Floors | planned | 0 | Sanitaryware fit, radiators, pressure test to 1.5 bar, commissioning
P35 | 2nd Fix Electrical — Faceplates & Testing | Second Fix Electrical | Derek Walsh | ElecFit Electrical Contractors | 2025-11-17 | 2025-11-28 | P33 | Test Meter, RCD Tester | Sockets, Switches, Light Fittings, Consumer Unit | 2nd Fix Electrical & Test | All Floors | planned | 0 | Faceplates, consumer units, EV chargers, EICR testing, commissioning
P36 | Kitchen & Bathroom Fit-Out | Kitchen Installation | Maria Okonkwo | BuildServ Site Services | 2025-12-01 | 2025-12-12 | P34;P35 |  | Kitchen Units, Worktops, Tiles, Sanitary Ware | Fitted Kitchens & Bathrooms | All Floors | planned | 0 | 24 apartments: kitchen units, worktops, tiling, bathroom suites
P37 | Decoration — Internal Paint & Finishes | Internal Decoration | Maria Okonkwo | BuildServ Site Services | 2025-12-01 | 2025-12-19 | P33 |  | Emulsion Paint, Gloss, Primer, Caulk | Decorated Internal Finishes | All Floors | planned | 0 | Mist coat + 2 coats emulsion, gloss to all joinery, sealant to junctions
P38 | Building Control Inspection & Sign-Off | Statutory Inspection | Helen Marchetti | HM Architecture Ltd | 2025-12-22 | 2025-12-22 | P27;P36;P37 |  |  | Building Regulations Completion Certificate | Full Building | planned | 0 | Final Building Control inspection, commissioning certificates, EPC

## HOW_TO_USE
How to Import This Data into IoC Process Manager
STEP 1 | Open the IoC Process Manager in your browser: http://localhost:5000
STEP 2 | Click 'Import' on the Projects screen
STEP 3 | Enter project name: "Thornfield Court Residential Development"
STEP 4 | Copy the PROJECT_DATA sheet as CSV: File → Save As → CSV UTF-8
STEP 5 | Paste the CSV text into the import text area, or drag the .csv file
STEP 6 | Click Import — the app will create all 38 processes with correct IoC mapping
COLUMN MAPPING | How each column maps to the IoC ontology:
process_id | → ioc:hasInternalProcessMark (unique identifier)
name | → rdfs:label on the ioc:Process instance
method | → ioc:Method via ioc:hasMethod → ProcessDataState → hasMethodValue
actor | → ioc:Actor via ioc:hasActor → ProcessDataState → hasActorValue
actor_org | → vcard:hasOrganizationName on the ioc:Actor
start_date | → prov:startedAtTime on the ioc:Schedule
end_date | → prov:endedAtTime on the ioc:Schedule
predecessors | → ioc:hasPredecessor (semicolon-separated list of process IDs)
resources | → ioc:Resource via ioc:hasResource (semicolon-separated)
input_materials | → ioc:RawMaterial (subclass of ioc:Element) via ioc:hasInputElement
output_elements | → ioc:Element via ioc:hasOutputElement
space | → ioc:Location (subclass of ioc:Space) via ioc:hasInitialSpace
status | → ioc:Status boolean flags (isStarted, isFinished, isPaused, isReady, isCancelled)
progress | → Stored directly on the Process (not a formal ioc property, display only)
notes | → ioc:Information via ioc:hasInputInformation
VALID STATUS VALUES | planned ¦ ready ¦ started ¦ finished ¦ paused ¦ cancelled
PREDECESSORS | Separate multiple IDs with semicolons: P01;P03;P07
RESOURCES | Separate multiple resources with semicolons: Excavator; Crane; Pump